## Sheet1
[TaskMagic] Project Release Schedule
Team: CMPUT301W18T24
Project Start Date: Feb 14, 2018
|  | FEBRUARY |  | Part 2 Due | [9 empty] | Part 3 Due |  | MARCH | [7 empty] | Part 4 Due | [22 empty] | APRIL | [7 empty] | Part 5 Due
TaskID | Task | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
2 | Project Part 2
2.1 | Requirement Specification | bar: FEBRUARY 14 to Part 2 Due 16
2.2 | UI Mockup and Storyboard | bar: FEBRUARY 14 to Part 2 Due 16
2.3 | Release Planning | bar: FEBRUARY 14 to Part 2 Due 16
2.4 | Glossary and Information Sources | bar: FEBRUARY 14 to Part 2 Due 16
3 | Project Part 3
3.1 | Addressing Feedback | bar: Part 2 Due 21 to Part 2 Due 22
3.2 | OO Analysis and Design | bar: Part 2 Due 22 to Part 2 Due 25
3.3 | Unit Test | bar: Part 2 Due 22 to Part 2 Due 25
4 | Project Part 4
4.1 | Addressing Feedback | bar: Part 3 Due 28 to MARCH 1
4.2 | Code Base of Prototype | bar: MARCH 1 to MARCH 6
4.3 | Code Documentation | bar: MARCH 1 to MARCH 6
4.4 | Test Code | bar: MARCH 6
4.5 | OO Design | bar: MARCH 1 to MARCH 2
4.6 | Release Planning | bar: MARCH 6 to MARCH 7
4.7 | Reuse Statement | bar: MARCH 6 to MARCH 8
5 | Project Part 5
5.1 | Addressing Feedback | bar: MARCH 8 to Part 4 Due 9
5.2 | Code Base of Prototype | bar: Part 4 Due 11 to APRIL 1
5.3 | Code Documentation | bar: Part 4 Due 28 to APRIL 1
5.4 | Test Cases | bar: APRIL 2 to APRIL 4
5.5 | Requirement Specification | bar: MARCH 8 to Part 4 Due 10
5.6 | OO Design | bar: MARCH 8 to Part 4 Due 10
5.7 | Release Planning | bar: MARCH 8 to Part 4 Due 10
5.8 | Reuse Statement | bar: APRIL 3 to APRIL 4
5.9 | Demo Presentation | bar: APRIL 7 to APRIL 8
5.1 | Promotional Video | bar: APRIL 5 to APRIL 6