## Sheet1
CMPUT301W18T24 Release Planning
Dates | Project # | Tasks to do | Related User Stories | Dependent Use Cases | Developers Working on
mar3-10 | 4 | 1. Layout Design | None | None | Fanje Shen/Yuandi Wu
mar3-10 |  | Elastic Search | none | none | Hamdi/Shi Yan
mar3-10 |  | log in |  |  | Shi Yan
mar3-10 |  | 2. Add Tasks | US 01.01.01 |  | Harrold
mar3-10 |  | 3. View Tasklist | US 01.02.01, 05.02.01, 05.04.01, 06.01.01, 06.02.01 | 2 | Harrold
mar3-10 |  | 4. Edit Task | US 01.03.01, 05.06.01, 05.07.01 | 1 | Yipu Chen
mar3-10 |  | 5. Remove Task | US 01.04.01 | 1 | Yipu chen
mar10-17 |  | 5. View Detail | US 02.01.01, 05.05.01 | 2 | Hamdi
mar10-17 |  | 6. Search | US 04.01.01, 04.02.01 | 2 | Hamdi/Shi Yan
mar10-17 |  | 7. Set Status | US 02.02.01, 07.01.01, 07.02.01 | 1 | Yipu Chen
mar10-17 |  | 8. View Profile | US 03.01.01, 03.03.01 |  | Fanje Shen
mar10-17 |  | 9. Edit Profile | US 03.02.01 | 8 | Yuandi Wu
mar10-17 |  | testing |  |  | Hamdi/ Yuandi/Fanje Shen/Harrold/Yipu/Shi Yan
| 5 | 10. Bid on Task | US 03.02.01 | 2 | Harrold
march 20-30 |  | 11. Notify | US 05.03.01 |  | Yuandi
march 20-30 |  | 12. Draft task (offline functionality) | US 08.01.01 | 1 | Yuandi/harrold
march 20-30 |  | 13. Set photograph | US 09.01.01 | 1 | Fanje Shen
march 20-30 |  | 14. View photograph | US 09.02.01 | 1 | Fanji Shen
march 20-30 |  | 15. Restrict photograph size | US 09.03.01 |  | Hamdi/Yipu Chen
march 20-30 |  | 16. Set location | US 10.01.01 | 1 | Shi Yan
march 20-30 |  | 17. View location | US 10.02.01 | 5 | Shi Yan
march 20-30 |  | 18. Search via geo | US 10.03.01 | 6 | Hamdi/Yipu Chen
April 1-9 |  | Documentation |  |  | Hamdi/ Yuandi/Fanje Shen/Harrold/Yipu/Shi Yan
April 1-9 |  | Testing |  |  | Hamdi/ Yuandi/Fanje Shen/Harrold/Yipu/Shi Yan
April 1-9 |  | video |  |  | Harrold/Fanji